## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | US1/N1 | Developer | Understand the problem | I can search for relevant solutions | 1 |  | 2018-09-04
1 | US1/N2 | Developer | Understand user stories | I can search for dataset accordingly | 1 |  | 2018-09-04
1 | US1/N3 | Developer | Download module related to project | I can use them on project | 1 |  | 2018-09-04
1 | US1/N4 | Developer | Get authorization keys | I can fetch data for prediction | 1 |  | 2018-09-04
1 | US1/N5 | Developer | Create twitter api script | I can fetch real time data from twitter | 1 |  | 2018-09-04
1 | US1/N6 | Developer | Find website for dataset | I can use it | 1 |  | 2018-09-11
1 | US1/N7 | Developer | Download datasets from various sources | I can train model on it | 1 |  | 2018-09-12
1 | US1/N8 | Developer | Create list for positive and negative words | Find labels for dataset | 1 |  | 2018-09-14
1 | US1/N9 | Developer | Normalize and stem my data | I can simplify my dataset | 1 |  | 2018-09-14
1 | US1/N10 | Developer | Dictionary for my words |  | 1 |  | 2018-09-16
1 | US1/N11 | Developer | Do POS tagging on dataset | I can use them as features | 1 |  | 2018-09-16
1 | US1/N12 | Developer | Vectorize my processed data | I can train model on it | 1 |  | 2018-09-18
2 | US1/N13 | Developer | Train my data on naïve bayes model | I can test it's accuracy and performance | 2 |  | 2018-09-25
2 | US1/N14 | Developer | Train my data on logistic regression model | I can test it's accuracy and performance | 2 |  | 2018-09-25
2 | US1/N15 | Developer | Train my data on LDA model | I can test it's accuracy and performance | 2 |  | 2018-09-28
2 | US1/N16 | Developer | Train my data on Decision tree model | I can test it's accuracy and performance | 2 |  | 2018-10-02
2 | US1/N17 | Developer | Train my data on SVM model | I can test it's accuracy and performance | 2 |  | 2018-10-02
2 | US1/N18 | Developer | Train my data on random forest model | I can test it's accuracy and performance | 2 |  | 2018-10-05
2 | US1/N19 | Developer | Train my data on multi-layer perceptron | I can test it's accuracy and performance | 2 |  | 2018-10-05
2 | US1/N20 | Developer | Train my data on recurrent neural network | I can test it's accuracy and performance | 2 |  | 2018-10-07
2 | US1/N21 | Developer | Train my data on convolutional neural network | I can test it's accuracy and performance | 2 |  | 2018-10-09
3 | US1/N22 | Developer | Calculate accuracy, recall, fvalue and other performace measures | I can analyze and compare vairous models | 3 |  | 2018-10-16
3 | US1/N23 | Developer | Test model on different tradeoff values | I can select best model | 3 |  | 2018-10-18
3 | US1/N24 | Developer | Apply my trained model on user stories |  | 3 |  | 2018-10-18
3 | US1/N25 | Developer | Create GUI for the project | User can use system effortlessly | 3 |  | 2018-10-20
3 | US2/N1 | Standard User | Analyse the type of content by the people I follow | I can choose whether to still follow them without going through there feeds | 3 |  | 2018-10-21
3 | US2/N2 | Standard User | Identify hateful content from comments | I Can identify weather to reply it or not | 3 |  | 2018-10-22
3 | US2/N3 | Standard User | Check my content before posting it | I can analyse how it will affect the audience | 3 |  | 2018-10-23
4 | US3/N1 | Content Creater | Check the hatefull content form hashtags | I can see the reaction of public on the perticular topic(Hashtag) | 3 |  | 2019-01-10
4 | US3/N2 | Content Creater | Check for public openion on tweets | I can understand public reaction | 3 |  | 2019-01-11
4 | US3/N3 | Content Creater | See views of verified accounts | I can usderstand openien of celibrities | 3 |  | 2019-01-12
4 | US3/N4 | Content Creater | See supporters and constant haters | I can target my audience accordingly | 3 |  | 2019-01-13
4 | US4/N1 | Reviewer | Report undetected voilent content | User experience and project efficiency can be increased | 3 |  | 2019-01-14
4 | US1/N26 | Developer | Perform testing on project for vulnerabilities | we can prevent any data leaks | 4 |  | 2019-01-15

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Violent and abusive content detection on social media>
SB1/US1 | Understand the problem | SB1/D1/T1 | Breaking the problem and understanding each component | MK+AP+AR | COMPLETED | 2018-09-04
|  | SB1/D1/T2 | Searching for relavent solutions | MK+AP+AR | COMPLETED | 2018-09-04
|  | SB1/D1/T3 | Searching alternative approches | MK+AP+AR | COMPLETED | 2018-09-04
|  | SB1/D1/T4 | Analysing similar projects | MK+AP+AR | COMPLETED | 2018-09-04
SB1/US2 | Understand user stories | SB1/D2/T1 | Looking for various use cases | MK+AP+AR | COMPLETED | 2018-09-04
|  | SB1/D2/T2 | Discussion about user stories | MK+AP+AR | COMPLETED | 2018-09-04
|  | SB1/D2/T3 | Searching for type of data required | MK+AP+AR | COMPLETED | 2018-09-04
SB1/US3 | Download module related to project | SB1/D3/T1 | Finding modules required | MK+AP+AR | COMPLETED | 2018-09-04
|  | SB1/D3/T2 | Downloading and Installing the modules | MK+AP+AR | COMPLETED | 2018-09-04
SB1/US6 | Get authorization keys | SB1/D4/T1 | Registering application on social media developer portal | MK+AP+AR | COMPLETED | 2018-09-04
SB1/US7 | Create twitter api script | SB1/D5/T1 | Creating basic twitter script | MK+AP+AR | COMPLETED | 2018-09-04
|  | SB1/D5/T2 | Adding additional features and filters in the script | MK+AP+AR | COMPLETED | 2018-09-11
SB1/US27 | Find website for dataset | SB1/D6/T1 | Searching for reliable data sources | MK+AP+AR | COMPLETED | 2018-09-11
SB1/US27 | Download datasets from various sources | SB1/D7/T2 | Downloading datasets from github | MK | COMPLETED | 2018-09-12
|  | SB1/D7/T3 | Downloading datasets from kaggle | AP | COMPLETED | 2018-09-12
|  | SB1/D7/T4 | Downloading datasets from popular dataset sites | AR | COMPLETED | 2018-09-12
|  | SB1/D7/T5 | Downloading datasets from other sources | MK+AP+AR | COMPLETED | 2018-09-12
SB1/US150 | Create list for positive and negative words | SB1/D8/T1 | Categorizing words in dataset | MK+AP+AR | COMPLETED | 2018-09-14
|  | SB1/D8/T2 | Downloading lists from internet sources | MK+AP+AR | COMPLETED | 2018-09-14
SB1/US28 | Normalize and stem my data | SB1/D9/T1 | Applying normalization and stemming on data | MK+AP+AR | COMPLETED | 2018-09-14
SB1/US50 | Dictionary for my words | SB1/D10/T1 | Creating list of words with their synonyms | MK+AP+AR | COMPLETED | 2018-09-16
SB1/US53 | Do POS tagging on dataset | SB1/D11/T2 | Studing POS tagging | MK+AP+AR | IN PROGRESS | 2018-09-16
|  | SB1/D11/T3 | Applying POS on data in distributed form | MK+AP+AR | IN PROGRESS | 2018-09-16
SB1/US55 | Vectorize my processed data | SB1/D12/T1 | Studing Vectorizing methods | MK+AP+AR | COMPLETED | 2018-09-18
|  | SB1/D12/T2 | Applying and comparing various vectorizing methods | MK+AP+AR | COMPLETED | 2018-09-18
|  | SB1/D12/T3 | Selecting best method | MK+AP+AR | COMPLETED | 2018-09-18

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Understand the problem | Breaking the problem and understanding each component | MK+AP+AR
|  | Searching for relavent solutions | MK+AP+AR
|  | Searching alternative approches | MK+AP+AR
|  | Analysing similar projects | MK+AP+AR
2 | Understand user stories | Looking for various use cases | MK+AP+AR
|  | Discussion about user stories | MK+AP+AR
|  | Searching for type of data required | MK+AP+AR
3 | Download module related to project | Finding modules required | MK+AP+AR
|  | Downloading and Installing the modules | MK+AP+AR
4 | Get authorization keys | Registering application on social media developer portal | MK+AP+AR
5 | Create twitter api script | Creating basic twitter script | MK+AP+AR
|  | Adding additional features and filters in the script | MK+AP+AR
6 | Find website for dataset | Searching for reliable data sources | MK+AP+AR
7 | Download datasets from various sources | Downloading datasets from github | MK
|  | Downloading datasets from kaggle | AP
|  | Downloading datasets from popular dataset sites | AR
|  | Downloading datasets from other sources | MK+AP+AR
8 | Create list for positive and negative words | Categorizing words in dataset | MK+AP+AR
|  | Downloading lists from internet sources | MK+AP+AR
9 | Normalize and stem my data | Applying normalization and stemming on data | MK+AP+AR
10 | Dictionary for my words | Creating list of words with their synonyms | MK+AP+AR
11 | Do POS tagging on dataset | Studing POS tagging | MK+AP+AR
|  | Applying POS on data in distributed form | MK+AP+AR
12 | Vectorize my processed data | Studing Vectorizing methods | MK+AP+AR
|  | Applying and comparing various vectorizing methods | MK+AP+AR
|  | Selecting best method | MK+AP+AR
| MK | Mukul Kadel
| AP | Aaditya Pareek
| AR | Akshat Rajpurohit
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 26 | 26 | Tasks
2018-09-11 | 15 | 16
2018-09-12 | 13 | 16
2018-09-14 | 9 | 10
2018-09-16 | 7 | 7
2018-09-18 | 5 | 5
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Violent and abusive content detection on social media>
SB2/US1 | Train my data on naïve bayes model | SB2/D1/T1 | Studing naïve bayes model | MK+AP+AR | COMPLETED | 2018-09-25
|  | SB2/D1/T2 | Implementing naïve bayes model | MK+AP+AR | COMPLETED | 2018-09-25
|  | SB2/D1/T3 | Implementing naïve bayes model on project data | MK+AP+AR | COMPLETED | 2018-09-25
SB2/US2 | Train my data on logistic regression model | SB2/D2/T1 | Studing logistic regression model | MK+AP+AR | COMPLETED | 2018-09-25
|  | SB2/D2/T2 | Implementing logistic regression model | MK+AP+AR | COMPLETED | 2018-09-25
|  | SB2/D2/T3 | Implementing logistic regression model on project data | MK+AP+AR | COMPLETED | 2018-09-28
SB2/US3 | Train my data on LDA model | SB2/D3/T1 | Studing LDA model | MK+AP+AR | COMPLETED | 2018-09-28
|  | SB2/D3/T2 | Implementing LDA model | MK+AP+AR | COMPLETED | 2018-09-28
|  | SB2/D3/T3 | Implementing LDA model on project data | MK+AP+AR | COMPLETED | 2018-09-28
SB2/US4 | Train my data on Decision tree model | SB2/D4/T1 | Studing decision tree model | MK+AP+AR | COMPLETED | 2018-10-02
|  | SB2/D4/T2 | Implementing decision tree model | MK+AP+AR | COMPLETED | 2018-10-02
|  | SB2/D4/T3 | Implementing decision tree model on project data | MK+AP+AR | COMPLETED | 2018-10-02
SB2/US5 | Train my data on SVM model | SB2/D5/T1 | Studing SVM model | MK+AP+AR | COMPLETED | 2018-10-02
|  | SB2/D5/T2 | Implementing SVM model | MK+AP+AR | COMPLETED | 2018-10-02
|  | SB2/D5/T3 | Implementing SVM model on project data | MK+AP+AR | COMPLETED | 2018-10-05
SB2/US6 | Train my data on random forest model | SB2/D6/T1 | Studing random forest model | MK+AP+AR | COMPLETED | 2018-10-05
|  | SB2/D6/T2 | Implementing random forest model | MK+AP+AR | COMPLETED | 2018-10-05
|  | SB2/D6/T3 | Implementing random forest model on project data | MK+AP+AR | COMPLETED | 2018-10-05
SB2/US7 | Train my data on multi-layer perceptron | SB2/D7/T1 | Studing multi-level perceptron | MK+AP+AR | COMPLETED | 2018-10-05
|  | SB2/D7/T2 | Implementing multi-level perceptron | MK+AP+AR | COMPLETED | 2018-10-05
|  | SB2/D7/T3 | Implementing multi-level perceptron on project data | MK+AP+AR | COMPLETED | 2018-10-07
SB2/US8 | Train my data on recurrent neural network | SB2/D8/T1 | Studing recurrent neural network | MK+AP+AR | COMPLETED | 2018-10-07
|  | SB2/D8/T2 | Implementing recurrent neural network | MK+AP+AR | COMPLETED | 2018-10-07
|  | SB2/D8/T3 | Implementing recurrent neural network on project data | MK+AP+AR | COMPLETED | 2018-10-09
SB2/US9 | Train my data on convolutional neural network | SB2/D8/T1 | Studing convolutional neural network | MK+AP+AR | COMPLETED | 2018-10-09
|  | SB2/D8/T2 | Implementing convolutional neural network | MK+AP+AR | COMPLETED | 2018-10-09
|  | SB2/D8/T3 | Implementing convolutional neural network on project data | MK+AP+AR | COMPLETED | 2018-10-09

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Train my data on naïve bayes model | Studing naïve bayes model | MK+AP+AR
|  | Implementing naïve bayes model | MK+AP+AR
|  | Implementing naïve bayes model on project data | MK+AP+AR
2 | Train my data on logistic regression model | Studing logistic regression model | MK+AP+AR
|  | Implementing logistic regression model | MK+AP+AR
|  | Implementing logistic regression model on project data | MK+AP+AR
3 | Train my data on LDA model | Studing LDA model | MK+AP+AR
|  | Implementing LDA model | MK+AP+AR
|  | Implementing LDA model on project data | MK+AP+AR
4 | Train my data on Decision tree model | Studing decision tree model | MK+AP+AR
|  | Implementing decision tree model | MK+AP+AR
|  | Implementing decision tree model on project data | MK+AP+AR
5 | Train my data on SVM model | Studing SVM model | MK+AP+AR
|  | Implementing SVM model | MK+AP+AR
|  | Implementing SVM model on project data | MK+AP+AR
6 | Train my data on random forest model | Studing random forest model | MK+AP+AR
|  | Implementing random forest model | MK+AP+AR
|  | Implementing random forest model on project data | MK+AP+AR
7 | Train my data on multi-layer perceptron | Studing multi-level perceptron | MK+AP+AR
|  | Implementing multi-level perceptron | MK+AP+AR
|  | Implementing multi-level perceptron on project data | MK+AP+AR
8 | Train my data on recurrent neural network | Studing recurrent neural network | MK+AP+AR
|  | Implementing recurrent neural network | MK+AP+AR
|  | Implementing recurrent neural network on project data | MK+AP+AR
9 | Train my data on convolutional neural network | Studing convolutional neural network | MK+AP+AR
|  | Implementing convolutional neural network | MK+AP+AR
|  | Implementing convolutional neural network on project data | MK+AP+AR
| MK | Mukul Kadel
| AP | Aaditya Pareek
| AR | Akshat Rajpurohit
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-09-25 | 27 | 27 | Tasks
2018-09-28 | 22 | 24
2018-10-02 | 18 | 22
2018-10-05 | 13 | 17
2018-10-07 | 7 | 12
2018-10-09 | 4 | 7
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Violent and abusive content detection on social media>
SB3/US1 | Calculate accuracy, recall, fvalue and other performace measures | SB3/D1/T1 | Calculating accuracy, recall and fvalue | MK+AP+AR | COMPLETED | 2018-10-16
|  | SB3/D1/T2 | Searching for other performance measures and calculating them | MK+AP+AR | COMPLETED | 2018-10-16
SB3/US2 | Test model on different tradeoff values | SB3/D2/T1 | Testing models with different parameters | MK+AP+AR | COMPLETED | 2018-10-16
|  | SB3/D2/T2 | Testing Neural networks | MK | COMPLETED | 2018-10-16
|  | SB3/D2/T3 | Testing SVM, decision tree and random forest models | AP | COMPLETED | 2018-10-18
|  | SB3/D2/T4 | Testing Logistic regression, LDA and naïve bayes models | AR | COMPLETED | 2018-10-18
SB3/US3 | Apply my trained model on user stories | SB3/D3/T1 | Looking for various ways to apply trained model | MK+AP+AR | COMPLETED | 2018-10-18
SB3/US4 | Create GUI for the project | SB3/D4/T1 | Designing GUI for project | MK+AP+AR | COMPLETED | 2018-10-20
|  | SB3/D4/T2 | Finalizing GUI for project | MK+AP+AR | COMPLETED | 2018-10-20
|  | SB3/D4/T3 | Creating basic structure of GUI | MK+AP+AR | COMPLETED | 2018-10-20
SB3/US5 | Analyse the content of the person I want to follow | SB3/D5/T1 | Creating modifying twitter script to fetch this data | MK | COMPLETED | 2018-10-21
|  | SB3/D5/T2 | Creating GUI for user | AP | COMPLETED | 2018-10-21
|  | SB3/D5/T3 | Joining script with GUI | AR | COMPLETED | 2018-10-21
SB3/US6 | Identify hateful content from comments | SB3/D6/T1 | Creating modifying twitter script to fetch this data | MK | COMPLETED | 2018-10-22
|  | SB3/D6/T2 | Creating GUI for user | AP | COMPLETED | 2018-10-22
|  | SB3/D6/T3 | Joining script with GUI | AR | COMPLETED | 2018-10-22
SB3/US7 | Check my content before posting it | SB3/D7/T1 | Creating modifying twitter script to fetch this data | MK | COMPLETED | 2018-10-23
|  | SB3/D7/T2 | Creating GUI for user | AP | COMPLETED | 2018-10-23
|  | SB3/D7/T3 | Joining script with GUI | AR | COMPLETED | 2018-10-23

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Calculate accuracy, recall, fvalue and other performace measures | Calculating accuracy, recall and fvalue | MK+AP+AR
|  | Searching for other performance measures and calculating them | MK+AP+AR
2 | Test model on different tradeoff values | Testing models with different parameters | MK+AP+AR
|  | Testing Neural networks | MK
|  | Testing SVM, decision tree and random forest models | AP
|  | Testing Logistic regression, LDA and naïve bayes models | AR
3 | Apply my trained model on user stories | Looking for various ways to apply trained model | MK+AP+AR
4 | Create GUI for the project | Designing GUI for project | MK+AP+AR
|  | Finalizing GUI for project | MK+AP+AR
|  | Creating basic structure of GUI | MK+AP+AR
5 | Analyse the type of content by the people I follow | Creating modifying twitter script to fetch this data | MK
|  | Creating GUI for user | AP
|  | Joining script with GUI | AR
6 | Identify hateful content from comments | Creating modifying twitter script to fetch this data | MK
|  | Creating GUI for user | AP
|  | Joining script with GUI | AR
7 | Check my content before posting it | Creating modifying twitter script to fetch this data | MK
|  | Creating GUI for user | AP
|  | Joining script with GUI | AR
| MK | Mukul Kadel
| AP | Aaditya Pareek
| AR | Akshat Rajpurohit
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 19 | 19 | Tasks
2018-10-18 | 15 | 14
2018-10-20 | 12 | 10
2018-10-21 | 9 | 9
2018-10-22 | 7 | 6
2018-10-23 | 3 | 5
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Violent and abusive content detection on social media>
1 | Check the hatefull content form hashtags | S4/D1/T1 | Creating modifying twitter script to fetch this data | MK | NOT COMPLETED | 2019-01-10
|  | S4/D1/T2 | Creating GUI for user | AP | NOT COMPLETED | 2019-01-10
|  | S4/D1/T3 | Joining script with GUI | AR | NOT COMPLETED | 2019-01-10
2 | Check for public openion on tweets | S4/D2/T1 | Creating modifying twitter script to fetch this data | MK | NOT COMPLETED | 2019-01-11
|  | S4/D2/T2 | Creating GUI for user | AP | NOT COMPLETED | 2019-01-11
|  | S4/D2/T3 | Joining script with GUI | AR | NOT COMPLETED | 2019-01-11
3 | See views of verified accounts | S4/D3/T1 | Creating modifying twitter script to fetch this data | MK | NOT COMPLETED | 2019-01-12
|  | S4/D3/T2 | Creating GUI for user | AP | NOT COMPLETED | 2019-01-12
|  | S4/D3/T3 | Joining script with GUI | AR | NOT COMPLETED | 2019-01-12
4 | See supporters and constant haters | S4/D4/T1 | Creating modifying twitter script to fetch this data | MK | NOT COMPLETED | 2019-01-13
|  | S4/D4/T2 | Creating GUI for user | AP | NOT COMPLETED | 2019-01-13
|  | S4/D4/T3 | Joining script with GUI | AR | NOT COMPLETED | 2019-01-13
5 | Report undetected voilent content | S4/D5/T1 | Creating GUI for user | AR | NOT COMPLETED | 2019-01-13
|  | S4/D5/T2 | Creating admin panel for reviewing reports | AP | NOT COMPLETED | 2019-01-14
|  | S4/D5/T3 | Creating script to monitor reported content | MK | NOT COMPLETED | 2019-01-14
6 | Perform testing on project for vulnerabilities | S4/D6/T1 | Testing various aspects of website | MK+AP+AR | NOT COMPLETED | 2019-01-14
|  | S4/D6/T2 | Creating test cases | MK | NOT COMPLETED | 2019-01-15
|  | S4/D6/T3 | Testing cases | AP+AR | NOT COMPLETED | 2019-01-15

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Check the hatefull content form hashtags | Creating modifying twitter script to fetch this data | MK
|  | Creating GUI for user | AP
|  | Joining script with GUI | AR
2 | Check for public openion on tweets | Creating modifying twitter script to fetch this data | MK
|  | Creating GUI for user | AP
|  | Joining script with GUI | AR
3 | See views of verified accounts | Creating modifying twitter script to fetch this data | MK
|  | Creating GUI for user | AP
|  | Joining script with GUI | AR
4 | See supporters and constant haters | Creating modifying twitter script to fetch this data | MK
|  | Creating GUI for user | AP
|  | Joining script with GUI | AR
5 | Report undetected voilent content | Creating GUI for user | AR
|  | Creating admin panel for reviewing reports | AP
|  | Creating script to monitor reported content | MK
6 | Perform testing on project for vulnerabilities | Testing various aspects of website | MK+AP+AR
|  | Creating test cases | MK
|  | Testing cases | AP+AR
| MK | Mukul Kadel
| AP | Aaditya Pareek
| AR | Akshat Rajpurohit
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 18 | 18 | Tasks
2019-01-11 | 15 | 18
2019-01-12 | 12 | 18
2019-01-13 | 8 | 18
2019-01-14 | 3 | 18
2019-01-15 | 1 | 18
Days