## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | US1/N1 | Standard User | Analyse the type of content by the people I follow | I can choose weather to still follow them without going through there feeds
1 | US1/N2 | Standard User | Identify hateful content from comments | I Can identify weather to reply it or not
1 | US1/N3 | Standard User | Check my content before posting it | I can analyse how it will affect the audience
1 | US2/N1 | Content Creater | Check the hatefull content form hashtags | I can see the reaction of public on the perticular topic(Hashtag)
1 | US2/N2 | Content Creater | Check for public openion on tweets | I can understand public reaction
1 | US2/N3 | Content Creater | See views of verified accounts | I can usderstand openien of celibrities
1 | US2/N4 | Content Creater | see supporters and constant haters | I can target my audience accordingly
1 | US3/N4 | Reviewer | Report undetected voilent content | User experience and project efficiency can be increased
1 | US4/N1 | Developer | Understand the problem | I can search for relevant solutions
1 | US4/N2 | Developer | Understand user stories | I can search for dataset accordingly
| US4/N3 | Developer | Download module related to project
| US4/N4 | Developer | Get authorization keys | I can fetch data for prediction
| US4/N5 | Developer | Create twitter api script | I can fetch real time data from twitter
| US4/N6 | Developer | Find website for dataset | I can use it
| US4/N7 | Developer | Download datasets from various sources | I can train model on it
| US4/N8 | Developer | create list for positive and negative words | Find labels for dataset
| US4/N9 | Developer | Normalize and stem my data | I can simplify my dataset
| US4/N10 | Developer | Dictionary for my words
| US4/N11 | Developer | Do POS tagging on dataset | I can use them as features
| US4/N12 | Developer | vectorize my processed data | I can train model on it
| US4/N13 | Developer | Train my data on naïve bayes model | I can test it's accuracy and performance
| US4/N14 | Developer | Train my data on logistic regression model | I can test it's accuracy and performance
| US4/N15 | Developer | Train my data on logistic regression model | I can test it's accuracy and performance
| US4/N16 | Developer | Train my data on Decision tree model | I can test it's accuracy and performance
| US4/N17 | Developer | Train my data on SVM model | I can test it's accuracy and performance
| US4/N18 | Developer | Train my data on random forest model | I can test it's accuracy and performance
| US4/N19 | Developer | Train my data on multi-layer perceptron | I can test it's accuracy and performance
| US4/N20 | Developer | Train my data on recurrent neural network | I can test it's accuracy and performance
| US4/N21 | Developer | Train my data on convolutional neural network | I can test it's accuracy and performance
| US4/N22 | Developer | Calculate accuracy, recall, fvalue and other performace measures | I can analyze and compare vairous models
| US4/N23 | Developer | Test model on different tradeoff values | I can select best model
| US4/N24 | Developer | Apply my trained model on user stories
| US4/N25 | Developer | Create GUI for the project | User can use system effortlessly
| US4/N26 | Developer | Perform testing on project for vulnerabilities | we can prevent any data leaks

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 |  | SB1/D1/T1
SB1/D1/T2
SB1/D1/T3
SB1/D1/T4
SB1/D1/T5
SB1/D1/T6
SB1/US2 |  | SB1/D2/T1
SB1/D2/T2
SB1/D2/T3
SB1/D2/T4
SB1/D2/T5
SB1/US3 |  | SB1/D3/T1
SB1/D3/T2
SB1/D3/T3
SB1/D3/T4
SB1/US6 |  | SB1/D4/T1
SB1/D4/T2
SB1/D4/T3
SB1/D4/T4
SB1/D4/T5
SB1/US7 |  | SB1/D5/T1
SB1/D5/T2
SB1/D5/T3
SB1/D5/T4
SB1/US27 |  | SB1/D6/T1
SB1/D6/T2
SB1/D6/T3
SB1/D6/T4
SB1/D6/T5
SB1/US27 |  | SB1/D7/T2
SB1/D7/T3
SB1/D7/T4
SB1/D7/T5
SB1/US150 |  | SB1/D8/T1
SB1/D8/T2
SB1/D8/T3
SB1/D8/T4
SB1/US28 |  | SB1/D9/T1
SB1/D9/T2
SB1/D9/T3
SB1/D9/T4
SB1/D9/T5
SB1/US50 |  | SB1/D10/T1
SB1/D10/T2
SB1/D10/T3
SB1/D10/T4
SB1/D10/T5
SB1/US53 |  | SB1/D11/T2
SB1/D11/T3
SB1/D11/T4
SB1/D11/T5
SB1/US55 |  | SB1/D12/T1
SB1/D12/T2
SB1/D12/T3
SB1/D12/T4
SB1/US51 |  | SB1/D13/T1
SB1/D13/T2
SB1/D13/T3
SB1/D13/T4
SB1/D13/T5
SB1/US70 |  | SB1/D14/T1
SB1/D14/T2
SB1/D14/T3
SB1/D14/T4
SB1/D14/T5
SB1/US71 |  | SB1/D15/T2
SB1/D15/T3
SB1/D15/T4
SB1/D15/T5
SB1/US72 |  | SB1/D16/T1
SB1/D16/T2
SB1/D16/T3
SB1/D16/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
| Add Department | SB2/D1/T1 | Designing the GUI | SP
|  | SB2/D1/T2 | Connection with database to fetch the data | RA
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TA into the application(using poornima email account) | SB2/D2/T1 | Designing of GUI | PB
|  | SB2/D2/T2 | Validating user input at client level | RM
|  | SB2/D2/T3 | Validating user input at server level | SP
|  | SB2/D2/T4 | Connection with Database to insert the record. | RA
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TA Receiving Confirmation Email | SB2/D3/T1 | Designing of Email(to be send) | PB
|  | SB2/D3/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D3/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TO into the application(using poornima email account) | SB2/D4/T1 | Designing of GUI | PB
|  | SB2/D4/T2 | Validating user input at client level | RM
|  | SB2/D4/T3 | Validating user input at server level | SP
|  | SB2/D4/T4 | Connection with Database to insert the record. | RA
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TO Receiving Confirmation Email | SB2/D5/T1 | Designing of Email(to be send) | PB
|  | SB2/D5/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D5/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D5/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Add Subject | SB2/D6/T1 | Designing of GUI | PB
|  | SB2/D6/T2 | Validating user input at client level | RM
|  | SB2/D6/T3 | Validating user input at server level | SP
|  | SB2/D6/T4 | Connection with Database to insert the record. | RA
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register Timetable Co-ordinator into the application | SB2/D7/T1 | Designing of GUI | PB
|  | SB2/D7/T2 | Validating user input at client level | RM
|  | SB2/D7/T3 | Validating user input at server level | SP
|  | SB2/D7/T4 | Connection with Database to insert the record. | RA
|  | SB2/D7/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Timetable Co-ordinator Receiving Confirmation Email | SB2/D8/T1 | Designing of Email(to be send) | PB
|  | SB2/D8/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D8/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days